## Sheet1
Risk ID | Risk | Treatment Action | Owner | Due Date | Status
R001 | Phishing | Enable MFA | IT Manager | 30/06/2026 | Planned
R002 | Unauthorized Access | Password Policy | IT Manager | 30/06/2026 | Planned
R003 | Laptop Theft | Enable BitLocker | IT Manager | 15/06/2026 | Planned
R004 | Data Leakage | Quarterly Access Reviews | HR Manager | 30/06/2026 | Planned
R005 | Email Compromise | Security Awareness Training | IT Manager | 15/06/2026 | Planned
R006 | SharePoint Permissions | RBAC Implementation | IT Manager | 30/06/2026 | Planned
R007 | VPN Credential Theft | MFA Deployment | IT Manager | 15/06/2026 | Planned
R008 | Website Defacement | Monthly Patching | IT Manager | 15/06/2026 | Planned
R009 | Social Engineering | Awareness Campaign | HR Manager | 30/06/2026 | Planned
R010 | Mobile Phone Loss | Mobile Device Management | IT Manager | 30/06/2026 | Planned